## CRM
Project Name | SMB CRM
Project Manager | Saurabh Agrawal
Start Date
End Date
Overall Progress | Initial
SR. No. | Task Name | Task Details | Min Hours | Max Hours | Status | Developer's Comment
1 | Database Design | Need to design required tables to store all the data in a relational form. | 8 | 10 | TBS
2 | LDAP Login | Integration of Ldap | 4 | 6 | TBS
3 | Dashboard | It will show the logged user info. | 6 | 8 | TBS
| Master Development | Layout
4 | Menu Master | Add new | 4 | 6 | TBS
|  | Edit | 4 | 6 | TBS
|  | View all | 4 | 6 | TBS
5 | User Master | Add new | 4 | 6 | TBS
|  | Edit | 4 | 6 | TBS
|  | View all | 4 | 6 | TBS
6 | Role Master | Add new | 4 | 6 | TBS
|  | Edit | 4 | 6 | TBS
|  | View all | 4 | 6 | TBS
7 | Roles Rights | Add new | 4 | 6 | TBS
|  | Edit | 4 | 6 | TBS
|  | View all | 4 | 6 | TBS
8 | Manage Modules | Add new | 4 | 6 | TBS
|  | Edit | 4 | 6 | TBS
|  | View all | 4 | 6 | TBS
9 | Campaign Master | Add new | 4 | 6 | TBS
|  | Edit | 4 | 6 | TBS
|  | View all | 4 | 6 | TBS
10 | TFNDID Master | Add new | 4 | 6 | TBS
|  | Edit | 4 | 6 | TBS
|  | View all | 4 | 6 | TBS
11 | DL Master | Add new | 4 | 6 | TBS
|  | Edit | 4 | 6 | TBS
|  | View all | 4 | 6 | TBS
12 | Country Master | Add new | 4 | 6 | TBS
|  | Edit | 4 | 6 | TBS
|  | View all | 4 | 6 | TBS
13 | Product Master | Add new | 4 | 6 | TBS
|  | Edit | 4 | 6 | TBS
|  | View all | 4 | 6 | TBS
14 | Reseller Master | Add new | 4 | 6 | TBS
|  | Edit | 4 | 6 | TBS
|  | View all | 4 | 6 | TBS
15 | End user Master | Add new | 4 | 6 | TBS
|  | Edit | 4 | 6 | TBS
|  | View all | 4 | 6 | TBS
16 | Client Master | Add new | 4 | 6 | TBS
|  | Edit | 4 | 6 | TBS
|  | View all | 4 | 6 | TBS
17 | Reporting Module | Add new | 4 | 6 | TBS
|  | Edit | 4 | 6 | TBS
|  | View all | 4 | 6 | TBS
| Control panel | Layout
18 | Configuration page |  | 8 | 10 | TBS
19 | Developer Testing |  | 15 | 20 | TBS
20 | UAT |  |  |  | TBS
| Total Estimate |  | 209 | 306

## Ticketing System
Project Name
Project Manager
Start Date
End Date
Overall Progress | Initial
SR. No. | Task Name | Task Details | Min Hours | Max Hours | Status | Developer's Comment
1
2
3
| Master Development | Layout
Total Estimate